## Critical Path Analysis
Task |  | Duration | ESD | LED
Start | A | 1 | 0 | 1
Item | B | 2 | 1 | 3
User | C | 3 | 1 | 3
Catalog | D | 4 | 3 | 7
Cart | E | 3 | 3 | 6
Personalised Recommendation | F | 4 | 7 | 13
Payment | G | 4 | 6 | 10
Order | H | 2 | 6 | 10
Delivery | I | 2 | 10 | 13
Retour Management | J | 3 | 10 | 13
Finish | K | 2 | 13 | 16

## Risky Path Analysis
|  | OT | LT | PT | ET | S_nominator | S_denominator | S | S^2 | Node SP | Final Node | Path (one per row) | Path sum of squares | Path Stdev | Risky path? (only for final paths) | LT Path | PT Path | Worst case delay (only for risky paths)
Start | A | 1 | 1 | 1 | 1 | 0 | 6 | 0 | 0 | 0 | B | A-B | 0 | 0 |  | 3 | 3
Item | B | 2 | 2 | 2 | 2 | 0 | 6 | 0 | 0 | 0 | C | A-C | 0.027778 | 0.16667 |  | 4 | 5
User | C | 3 | 3 | 4 | 3.1667 | 1 | 6 | 0.16667 | 0.027778 | 0.16667 | D | A-B-D | 0.027778 | 0.16667 |  | 7 | 8
Catalog | D | 4 | 4 | 5 | 4.1667 | 1 | 6 | 0.16667 | 0.027778 | 0.2357 | D | A-C-D | 0.055556 | 0.2357 |  | 8 | 10
Cart | E | 2 | 3 | 3 | 2.8333 | 1 | 6 | 0.16667 | 0.027778 | 0.16667 | E | A-B-E | 0.027778 | 0.16667 |  | 7 | 8
Personalised Recommendation | F | 3 | 4 | 6 | 4.1667 | 3 | 6 | 0.5 | 0.25 | 0.55277 | F | A-B-F | 0.25 | 0.5 |  | 7 | 9
Payment | G | 4 | 4 | 7 | 4.5 | 3 | 6 | 0.5 | 0.25 | 0.52705 | F | A-C-F | 0.27778 | 0.52705 |  | 8 | 11
Order | H | 1 | 2 | 2 | 1.8333 | 1 | 6 | 0.16667 | 0.027778 | 0.2357 | F | A-B-D-F | 0.27778 | 0.52705 |  | 11 | 14
Delivery | I | 1 | 2 | 2 | 1.8333 | 1 | 6 | 0.16667 | 0.027778 | 0.55277 | F | A-C-D-F | 0.30556 | 0.55277 |  | 12 | 16
Retour Management | J | 3 | 3 | 4 | 3.1667 | 1 | 6 | 0.16667 | 0.027778 | 0.55277 | G | A-B-E-G | 0.27778 | 0.52705 |  | 10 | 13
Finish | K | 2 | 2 | 2 | 2 | 0 | 6 | 0 | 0 | 0.55277 | H | A-B-E-H | 0.055556 | 0.2357 |  | 8 | 8
[11 empty] | I | A-B-E-G-I | 0.30556 | 0.55277 |  | 12 | 15
[11 empty] | I | A-B-E-H-I | 0.083333 | 0.28868 |  | 10 | 10
[11 empty] | J | A-B-E-G-J | 0.30556 | 0.55277 |  | 13 | 17
[11 empty] | J | A-B-E-H-J | 0.083333 | 0.28868 |  | 11 | 12
[11 empty] | K | A-B-F-K | 0.25 | 0.5 | no | 9 | 11
[11 empty] | K | A-C-F-K | 0.27778 | 0.52705 | no | 10 | 13
[11 empty] | K | A-B-D-F-K | 0.27778 | 0.52705 | no | 13 | 16
[11 empty] | K | A-C-D-F-K | 0.30556 | 0.55277 | yes | 14 | 18 | 4
[11 empty] | K | E-B-E-G-I-K | 0.30556 | 0.55277 | yes | 14 | 17 | 3
[11 empty] | K | A-B-E-H-I-K | 0.083333 | 0.28868 | no | 12 | 12
[11 empty] | K | A-B-E-G-J-K | 0.30556 | 0.55277 | no | 15 | 19
[11 empty] | K | A-B-E-H-J-K | 0.083333 | 0.28868 | no | 13 | 14